## Sheet1
|  | Project Start Date: | 2025-09-16 |  | Project Current Date: | 2025-09-24 |  |  |  | Lurry |  | Monish |  | Joseph |  | All | Cornelius
|  | Project Members & Roles: | Monish , Lurry , Cornelius , Joseph
|  | Project Title: | Enter project name
[9 empty] | September '25 | [14 empty] | October '25 | [30 empty] | November '25
 | time axis 2025-09-16 to 2025-11-18
# |  | Task | Assigned To | Start | End | Days | Status | % Done | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
CW1 | Planning
|  | Team Discussion 1 | All | 2025-09-17 | 2025-09-17 | 1 | Completed | bar: 2025-09-17
|  | Create Whatsapp Group | Joseph | 2025-09-17 | 2025-09-17 | 1 | Completed | bar: 2025-09-17
|  | Create and Link Trello Board | Joseph | 2025-09-17 | 2025-09-24 | 6 | Completed | bar: 2025-09-24
|  | Create Excel Gnatt Chart | Joseph | 2025-09-23 | 2025-09-24 | 2 | In Progress | bar: 2025-09-24
|  | Create & Setup Github | Joseph | 2025-09-23 | 2025-09-25 | 3 | Final Touches | bar: 2025-09-25
|  | Team Discussion 2 | All | 2025-09-24 | 2025-09-24 | 1 | Pending | bar: 2025-09-24
|  | Create Work Breakdown Structure | Joseph | 2025-09-24 | 2025-09-26 | 3 | Pending | bar: 2025-09-26
Report
|  | Collate Team member signatures | All | 2025-09-24 | 2025-09-24 | 1 | Completed | bar: 2025-09-24
|  | Setup Table of contents | Joseph | 2025-09-23 | 2025-09-24 | 2 | Starting | bar: 2025-09-24
|  | 1.6-1.9 | Joseph | 2025-09-24 | 2025-10-05 |  | Pending | bar: 2025-10-05
|  | 1.1-1.2 | Lurry | 2025-09-24 | 2025-10-05 |  | Pending | bar: 2025-10-05
|  | 1.3 | Cornelius | 2025-09-24 | 2025-10-05 |  | Pending | bar: 2025-10-05
|  | 1.4-1.5 | Monish | 2025-09-24 | 2025-10-05 |  | Pending | bar: 2025-10-05
CW2
Legend: